GRAPH SWARM

# Research Execution Plan

Three research rollouts for an eight-week Graph Swarm experiment

| Status | ACTIVE - current research scope |
| --- | --- |
| Last updated | 14 August 2026 |
| Authority | Canonical plan for what the team is building now, in what order, and how each rollout is accepted. |

Source-of-truth rule: Use this document only for the authority stated above. When it conflicts with a newer entry in the Research Ledger, the Ledger wins. Future-production material must not be treated as current research scope.

# Contents

This is a static navigation map intended for human readers and GPT source retrieval. Section numbers are stable unless a major revision is made.

1  Project definition and research boundary

2  Research question, hypotheses, and claims

3  Experimental system architecture

4  Domain model and graph schema

5  Rollout 1 - Observe & Remember

6  Rollout 2 - Advise & Prevent

7  Rollout 3 - Evaluate & Generalize

8  Eight-week execution schedule

9  Evaluation protocol

10  Interfaces and data contracts

11  Risks, stop conditions, and scope control

12  Final research artifacts and definition of done

# 1. Project definition and research boundary

Graph Swarm is currently an experimental research system for studying whether agent workflows can reuse empirically verified failure experience across executions. The project is not being developed as a production agent platform during the eight-week research window.

Frozen two-month objective: Demonstrate, with a reproducible benchmark, whether a past failure and its verified recovery can be retrieved before a related future action and reduce recurrence of that failure without producing excessive false advice.

## 1.1 Problem statement

Agentic software-engineering workflows often rediscover the same operational failures across runs. A previous execution may already have exposed an invalid parameter, incompatible dependency, configuration mistake, tool limitation, or test-environment issue, yet a later agent can repeat the same costly path because the earlier experience is not represented as actionable operational memory.

## 1.2 Current contribution boundary

The contribution is not "using a graph for agent memory". Graph, temporal, and adaptive agent memories already have substantial prior work.

The proposed mechanism is Verified Failure Memory: historical experience influences a future action based on evidence that a recovery worked under comparable conditions.

Neo4j is the implementation substrate for structured operational memory, not the research contribution by itself.

A coding/DevOps agent is the experimental subject because tests, exit codes, API responses, and build results provide objective outcome signals.

Causal or interventional claims are deferred unless later experiments include controlled counterfactual replay or equivalent causal identification.

## 1.3 Explicitly out of scope for the eight-week study

Production SaaS deployment, authentication, tenancy, billing, autoscaling, or high availability.

Large React graph dashboards or real-time visualization as a primary deliverable.

Autonomous recovery or silent modification of tool calls.

Support for multiple agent frameworks.

Graph Data Science centrality as an orchestration policy.

General contradiction negotiation across arbitrary agent beliefs.

A claim that graph memory is universally better than vector memory.

# 2. Research question, hypotheses, and claims

## 2.1 Primary research question

RQ1: Does retrieval of empirically verified historical failure resolutions reduce recurring failures in agentic software-engineering workflows compared with the same agent without persistent failure memory?

## 2.2 Secondary questions

RQ2: Does environment-aware matching reduce incorrect or stale recovery advice?

RQ3: Does outcome verification improve transfer quality compared with retrieving unverified historical incidents?

RQ4: What is the latency and context-cost overhead of Graph Swarm relative to the improvement it produces?

## 2.3 Falsifiable hypotheses

| ID | Hypothesis | Evidence required |
| --- | --- | --- |
| H1 | Verified Failure Memory lowers Repeated Failure Rate on recurrence opportunities. | Paired chronological benchmark; same model, prompt, tools, and task order. |
| H2 | Outcome verification lowers False Advice Rate relative to unverified incident retrieval. | Ablation or controlled comparison with verification removed. |
| H3 | Environment/version matching reduces transfer mistakes when tool or dependency state changes. | Cases with intentionally shifted versions/configuration plus ablation. |

## 2.4 Claims we are allowed to make only after evidence

"Graph Swarm reduced repeated known failures by X percentage points on our recurrence benchmark" only after the controlled experiment.

"Verification contributes to the improvement" only after the verification ablation.

"The result generalizes" only after testing additional repositories/failure families not used for tuning.

Do not use "first-of-its-kind", "causal", or "state of the art" without direct evidence and a literature check at publication time.

# 3. Experimental system architecture

The experimental agent is deliberately small. Graph Swarm must remain separable from the agent framework so the research mechanism is independently testable.

Groq-hosted model
        |
        v
PydanticAI minimal coding agent
        |
        | planned tool action
        v
Graph Swarm pre-execution check
        |
        +---- no applicable incident ----> execute tool
        |
        +---- applicable verified recovery -> inject concise advice -> agent reconsider
        |
        v
Tool result / test outcome
        |
        v
Failure detector + resolution evidence
        |
        v
Neo4j operational memory

## 3.1 Experimental agent

Framework: PydanticAI, selected for direct Groq support, typed tool interfaces, and lifecycle hooks.

Model provider: Groq. Freeze one model for the main experiment. Any model change creates a new experiment configuration.

Initial tools: read_file, write_file, run_tests, run_command, plus one deterministic/mock API tool if needed for parameter/configuration failures.

The agent is not a product deliverable. Its only job is to provide reproducible actions, failures, retries, and objective outcomes.

## 3.2 Event capture

For the research prototype, use a simple typed event model emitted from agent/tool hooks. OpenTelemetry can be added as an export path later, but it is not required to prove the core mechanism.

| Field group | Minimum contents |
| --- | --- |
| Identity | run_id, task_id, action_id, timestamp |
| Agent/model | framework, model, prompt_version, temperature/settings |
| Action | tool, operation, normalized arguments/signature |
| Environment | repository, dependency/tool version, runtime markers |
| Result | status, exit_code/HTTP code, exception class, normalized error |
| Outcome | task success, tests passed, evaluator result, retries/tool calls |

# 4. Domain model and graph schema

## 4.1 Core entities

| Node | Purpose | Key properties |
| --- | --- | --- |
| Run | One agent execution of a task. | id, task_id, started_at, model_config, final_status |
| Task | The software-engineering objective. | id, family_id, repository, chronological_index |
| Action | A concrete tool or agent action. | id, operation, timestamp, status, attempt |
| Tool | Execution asset used by the action. | name, version/type |
| FailureEpisode | Normalized operational failure. | id, failure_type, signature, symptom, observed_at |
| Resolution | A change associated with recovery. | id, description, status, evidence counts |
| Outcome | Externally evaluated result. | success, tests_passed, exit_code, timestamp |
| Environment | Applicability context. | runtime, tool/dependency versions, repository metadata |

## 4.2 Core relationships

(Task)-[:HAS_ACTION]->(Action)
(Action)-[:USED]->(Tool)
(Action)-[:PART_OF]->(Run)
(Action)-[:PART_OF_FAILURE]->(FailureEpisode)
(FailureEpisode)-[:OCCURRED_IN]->(Environment)
(FailureEpisode)-[:RESOLVED_BY]->(Resolution)
(Resolution)-[:VERIFIED_BY]->(Outcome)
(FailureEpisode)-[:SIMILAR_TO]->(FailureEpisode)  # optional derived edge

Methodological rule: A successful action after a change is evidence for a candidate resolution. It is not automatically proof that the change caused the success. Keep resolution confidence separate from any future causal confidence.

# 5. Rollout 1 - Observe & Remember

Research milestone: prove that failures and recoveries can be represented faithfully and persist across runs.

| Area | Work in this rollout | Outcome / acceptance evidence |
| --- | --- | --- |
| Minimal agent | Groq + PydanticAI agent with a small tool set and deterministic evaluators. | At least several controlled tasks execute end-to-end and can fail/recover reproducibly. |
| Failure detection | Deterministic rules for test, command, dependency, configuration, and tool-parameter failures. | Known injected failures map to expected normalized classes. |
| Operational graph | Persist Run, Task, Action, Tool, FailureEpisode, Environment, Resolution, Outcome. | Graph survives restart and reconstructs the execution lineage. |
| Resolution evidence | Record change between failed attempt and later success as candidate/observed recovery. | One complete failure -> resolution -> successful outcome chain is queryable. |
| Research hygiene | Version prompts, model settings, task fixtures, schemas, and code. | A run can be reproduced from configuration and task identifiers. |

## 5.1 Rollout 1 exit gate

Agent executes task
   -> tool/action fails
   -> failure is normalized
   -> FailureEpisode is stored
   -> agent changes something
   -> objective evaluator reports success
   -> Resolution + Outcome are linked and persisted

Gate R1: Do not begin intelligent recurrence retrieval until the stored history is correct enough to reconstruct what actually happened.

# 6. Rollout 2 - Advise & Prevent

Research milestone: prove that memory can change a future action before the same failure is repeated.

## 6.1 Recurrence candidate generation

Filter structurally by tool/operation, normalized failure family, and compatible environment.

Use semantic similarity only where structured fields do not sufficiently identify related variants.

Retrieve the historical resolution plus its evidence and applicability conditions, not the full historical trace.

Apply staleness/version checks before advising the agent.

## 6.2 Runtime advisory contract

evaluate_action(current_action, environment) -> {
  risk_level,
  matched_incident_id,
  applicability_score,
  recovery_summary,
  recovery_evidence,
  confidence,
  provenance
}

The advisory is injected before the selected tool executes. In the research version, Graph Swarm does not silently rewrite arguments or block execution. The agent may accept or ignore the advice, and that behavior is recorded.

## 6.3 Rollout 2 exit gate

Earlier task: Failure F -> Recovery R -> successful outcome
Later related task: agent plans action associated with F
Graph Swarm: retrieves F and verified/observed R before execution
Agent: changes plan/action
Objective evaluator: task succeeds without repeating F

Gate R2: This is the critical proof point. If historical memory cannot reliably change later behavior, stop and revise retrieval/applicability before expanding the benchmark.

# 7. Rollout 3 - Evaluate & Generalize

Research milestone: determine whether the mechanism works across a controlled recurrence benchmark, not just one demonstration.

## 7.1 Primary benchmark

Use one SWE-smith-derived recurring-failure benchmark. SWE-smith provides executable software-engineering environments and automatically generated test-breaking tasks; Graph Swarm adds a chronological recurrence structure on top of selected instances.

Create failure families rather than independent random tasks.

Manually validate transfer pairs/families. Manual validation is dataset QA, not a separate benchmark.

Order tasks chronologically. A task may use only history created by earlier tasks.

Separate any tuning/development families from final evaluation families where feasible.

Begin with roughly 15-30 validated tasks while debugging the methodology; scale only after the mechanism behaves correctly.

## 7.2 Experimental conditions

| Condition | Required? | Description |
| --- | --- | --- |
| B0 - No persistent memory | Yes | Identical agent with no cross-run operational memory. |
| B1 - Vector episodic memory | Recommended | Retrieve text summaries of previous incidents by semantic similarity. Required if the final claim compares against conventional episodic memory. |
| T - Graph Swarm | Yes | Structured failure memory + recovery evidence + environment applicability + pre-execution advice. |
| Ablation - no verification | If time | Same retrieval without outcome-verification signal. |
| Ablation - no environment matching | If time | Tests whether applicability context prevents stale/wrong advice. |

## 7.3 Rollout 3 exit gate

All primary task-family assignments are frozen before final runs.

Baseline and treatment use the same model, prompt, tools, task order, evaluator, and resource limits.

Repeated Failure Rate and False Advice Rate are reported with task-level evidence.

Questionable or anomalous runs are rerun under a documented rule rather than selectively discarded.

Limitations and negative results are reported.

# 8. Eight-week execution schedule

| Week | Focus | Research output / gate |
| --- | --- | --- |
| 1 | Literature freeze, experiment spec, minimal agent, first controlled tasks. | Runnable agent + versioned task/evaluator format. |
| 2 | Structured events, deterministic failure taxonomy, Neo4j schema. | Failures captured and queryable. |
| 3 | Resolution and outcome model; first complete memory chain. | Rollout 1 exit gate. |
| 4 | Recurrence signatures, candidate retrieval, applicability rules. | Historical incident retrieved for a related planned action. |
| 5 | Pre-execution advisory and first prevention demo. | Rollout 2 exit gate. |
| 6 | SWE-smith-derived recurrence dataset, manual QA, baseline implementations. | Benchmark frozen enough for final runs. |
| 7 | Main experiments, repeat runs, primary metrics, selected ablations. | Result tables + raw artifacts. |
| 8 | Analysis, error taxonomy, confidence intervals/tests, report/README cleanup. | Rollout 3 exit gate + research package. |

# 9. Evaluation protocol

## 9.1 Controlled variables

Model identifier and provider configuration

System/developer prompt version

Tool definitions and tool permissions

Temperature/reasoning settings and token budget

Task order and repository snapshot

Evaluator/tests

Timeouts and maximum action count

## 9.2 Primary metrics

| Metric | Definition / interpretation |
| --- | --- |
| Repeated Failure Rate (RFR) | Known recurring failures repeated / opportunities to repeat a previously known failure. Primary mechanism metric. |
| Task Success Rate | Tasks passing the objective evaluator / tasks attempted. |
| False Advice Rate | Incorrect or inapplicable recovery recommendations / total advice events. |
| Recovery Reuse Success | Advice-supported executions that succeed without the matched failure recurring / advice accepted. |
| Retries per Task | Number of recovery attempts; useful operational efficiency measure. |
| Tool Calls per Success | Tool invocations divided by successful tasks. |
| Context/Token Cost | Tokens added or consumed by memory/advice where provider data is available. |
| Retrieval Latency | Time added by Graph Swarm candidate retrieval and scoring. |
| Precision@1 incident | Whether the top retrieved incident belongs to the manually validated recurrence family. |

## 9.3 Statistical handling

Treat tasks as paired whenever the same task is run under baseline and treatment.

For binary task-success differences, use paired summaries and consider McNemar-style analysis if sample size supports it.

For RFR and false-advice rates, report counts, percentages, and bootstrap confidence intervals over tasks/families where practical.

Because LLM agents are stochastic, repeat unstable tasks under a pre-declared repetition rule. Do not selectively rerun only unfavorable outputs.

Report effect sizes and raw denominators, not only p-values.

# 10. Interfaces and data contracts

## 10.1 Minimal in-process API

record_event(event)
record_outcome(action_id, outcome)
record_resolution(failure_id, resolution, evidence)
evaluate_action(task, planned_action, environment) -> AdviceResult
get_incident(incident_id)

## 10.2 Design rule

Keep Graph Swarm behind a small interface even if the first implementation is a modular monolith. This allows the agent harness, Neo4j layer, scoring logic, and future production adapters to evolve independently.

# 11. Risks, stop conditions, and scope control

| Risk | Why it matters | Response / stop condition |
| --- | --- | --- |
| Failure families are not truly transferable | The benchmark would manufacture an advantage. | Manual family validation; discard ambiguous pairs before final runs. |
| Graph Swarm warns too often | RFR may improve by flooding the agent with advice. | Track False Advice Rate and advice coverage; calibrate threshold. |
| Recovery evidence is confounded | Success after a change may not be due to that change. | Use "verified/observed recovery" language; avoid causal claims. |
| Agent itself is unstable | Noise can dominate the memory effect. | Simplify tools/tasks; freeze model/config; repeat unstable cases. |
| Scope expands into product engineering | Two-month research schedule collapses. | Move integrations, dashboards, scaling, and autonomy to Future Production Plan. |
| No measurable improvement by Gate R2/R3 | Core hypothesis may be weak. | Analyze false matches and recurrence definition before adding features; report negative result if rigorous. |

# 12. Final research artifacts and definition of done

| Artifact | Definition of done |
| --- | --- |
| Reference implementation | Reproducible agent + Graph Swarm experiment code, pinned dependencies/configuration. |
| Benchmark package | Validated recurrence families, chronological ordering, objective evaluators, dataset notes. |
| Baselines | At minimum no-memory; vector episodic baseline if the final claim compares against episodic memory. |
| Raw results | Per-task runs, memory events, advice events, metrics, configuration hashes. |
| Analysis | Primary metrics, uncertainty, ablations where available, failure/error analysis. |
| Research report | Problem, prior work boundary, method, experiment, results, limitations, future work. |
| README/demo | One concise end-to-end example showing earlier failure -> learned recovery -> later prevention. |

Final success criterion: A reader should be able to reproduce the benchmark, see exactly when Graph Swarm had an opportunity to help, and verify whether the treatment changed behavior relative to the controlled baseline.